## How to use
Business Readiness Assessment
Are the people ready, not just the system
| What this is | The business half of go-live readiness, assessed as seriously as the technical half.
| Where it sits | The Change Impact Assessment says WHO is affected. The Business Adoption Plan says what will be DONE about it. This says whether it WORKED — and its answer is the 'business readiness assessed and passed' line in the Go-Live Readiness Assessment. Without this, that line is somebody's opinion.
| Five areas | Awareness, Capability, Process, Support, Commitment — plus Timing, which is the one nobody assesses and which sinks more go-lives than any of the others.
| Assess per group, not overall | 'The business is ready' is never true of everybody. Copy the rows per affected group if their readiness genuinely differs — one group at Red can be a go-live decision, an average of Amber cannot.
| Evidence, not assertion | 'Training delivered' means attendance confirmed. 'People can do it' means somebody watched them do it. A status with no evidence is flagged.
| Not applicable | Some rows genuinely will not apply. Say so, with a reason. Marking things N/A to make the number look better is how this becomes theatre.
| Change Specialists | EXPERIENCE ¦ KNOWLEDGE ¦ RESULTS
Where this sits
Comes from: The Business Adoption Plan.
Feeds: The Go-Live Readiness Assessment — delivery readiness is only half of it.
CS Template Library v1.0 · August 2026
Something wrong with this template? Tell us which one and what happened: backoffice@changespecialists.co.uk

## Summary
Readiness Summary
< How to use | Feeds the Go-Live Readiness Assessment.
| Area | Items | Red | Amber
Awareness
Capability
Process
Support
Commitment
Timing
Verdict
This is the answer the Go-Live Readiness Assessment is asking for on its business stream.
Controls
| Marked Done with no evidence |  |  |  | 'Training delivered' means attendance confirmed. Assertion is not evidence.
Nobody owns it
| Marked not applicable |  |  |  | Fine if genuine. A lot of these and the assessment stops meaning anything.
| Change Specialists | EXPERIENCE ¦ KNOWLEDGE ¦ RESULTS

## Readiness
Business Readiness Assessment
Evidence, not assertion. Assess per group.
< How to use
Ref | Area | What must be true | Group affected | Status | Evidence | Owner | By when | RAG
| Awareness | Everyone affected knows the change is coming and roughly when
| Awareness | They know why it is happening, not just that it is
| Awareness | They know where to go with a question
| Capability | Training has been delivered to everyone who needs it
| Capability | People can demonstrate the new task, not just attend the session
| Capability | Guidance exists and is findable at the moment of need
| Capability | Local champions or superusers are identified and briefed
| Process | Updated processes and procedures are published
| Process | Roles and responsibilities updated where they change
| Process | Handoffs to other teams have been agreed with those teams
| Process | Workarounds documented for anything not ready on day one
| Support | Day-one support is arranged and staffed
| Support | The service desk knows it is coming and how to handle it
| Support | There is a route to escalate a problem on day one
| Commitment | The business sponsor has confirmed the business is ready
| Commitment | Line managers are visibly behind it
| Commitment | Someone named owns adoption after go-live
| Commitment | Benefit measures are baselined so improvement can be shown
| Timing | The go-live date avoids the team's peak period
| Timing | Nothing else major lands on these people the same week