Choosing Your Delivery Approach

Waterfall, agile or hybrid — and how to tell which you need

EXPERIENCE  |  KNOWLEDGE  |  RESULTS

# The short answer

How much is genuinely unknown at the start? If very little is unknown, waterfall will be faster and cheaper. If a lot is unknown, agile will find it out sooner. Most real change sits between the two, which is why most real delivery is hybrid.

The choice is usually made on habit, or on whichever approach the last programme used. Neither is a reason. What follows is how to decide it properly, in about ten minutes.

# Waterfall

Plan the whole thing, then build it in sequence. Each stage finishes before the next begins.

It suits

Requirements that are genuinely known and stable.

Fixed regulatory or contractual deadlines with defined scope.

Work where the cost of changing direction later is very high — physical build, infrastructure, migrations.

Environments where an audit trail of formal approvals is required.

It struggles when

Nobody can describe the end state at the start.

The business will only know what it wants once it sees something.

The market or the policy behind the change is still moving.

# Agile

Build in short increments. Show something working, learn from it, and decide what to do next.

It suits

Requirements that will become clearer through use.

Products with real users whose feedback changes the answer.

Work that can be released in useful pieces.

Teams that can be kept together and dedicated.

It struggles when

The scope is genuinely fixed and the deadline is legal.

The business cannot free people to take part every sprint.

Nothing can be released until all of it is finished.

It is adopted as a label without changing how decisions get made.

# Hybrid

Governance, funding and stage gates run in a planned sequence. Delivery inside a stage runs in increments.

This is where most substantial change actually sits, and pretending otherwise causes more trouble than either pure approach. A board that needs a business case and a gate can still sit above a team that works in sprints.

It suits

Large programmes with a mix of certain and uncertain workstreams.

Organisations whose funding and approval cycles are fixed.

Change that includes both a system and a way of working.

# Deciding

Score each row. More marks on the left points to waterfall, more on the right points to agile, a spread points to hybrid.

| Question | Points to waterfall | Points to agile |
| --- | --- | --- |
| How well is the end state understood? | Clearly defined and agreed | Broadly known, detail will emerge |
| How likely is scope to change? | Low — it is fixed | High — it should change as we learn |
| Can it be released in pieces? | No — it is all or nothing | Yes — pieces are useful on their own |
| How available is the business? | Available at gates | Available continuously |
| What does the deadline look like? | Fixed date, fixed scope | Fixed date, flexible scope |
| What is the cost of a late change? | Very high | Manageable |
| How stable is the team? | Assembled per stage | Dedicated and kept together |

If the answers are split roughly down the middle, that is not a failure of the test. That is the test telling you the answer is hybrid.

# What does not change, whichever you choose

The approach decides how the work is sequenced. It does not decide whether the change succeeds. Three things apply to all three approaches.

|  | What it means | What it looks like in practice |
| --- | --- | --- |
| One Team | The right people, with a shared vision and shared values. | Strategists, gamechangers, implementers, polishers and orchestrators are different strengths. A team of one type fails predictably. |
| Business Adoption | Change only counts once people work differently. | A stream of business activity running alongside delivery, from the start — not a training course bolted on at the end. |
| Intelligent Delivery | Sequence the work by risk and business priority. | Clear priorities, governance that decides, testing that is proportionate, and go-live accepted by both delivery and the business. |

Go-live is accepted twice: once by delivery, once by the business. That single rule holds whichever approach you picked, and it is the one most often skipped.

# Which templates to use

| If you chose | Start with |
| --- | --- |
| Waterfall | Project Charter · Business Case · Requirements Specification · MoSCoW Prioritisation · Test Strategy · Go-Live Readiness Assessment · Post-Implementation Review |
| Agile | Product Vision and Roadmap · Product Backlog · User Story template · Definition of Ready and Done · Sprint Plan · Release Plan |
| Hybrid | Business Case and Stage Gates for governance, plus the agile set inside each stage |
| All three | RAID Log · Decision Log · Change Request Form · Status Report · Stakeholder Map · Business Adoption Plan · Benefits Tracker |

Where this sits

Comes from: Nothing — this is where you start when the approach is not yet decided.

Feeds: The Waterfall Delivery Guide, the Agile Delivery Guide or the Hybrid Delivery Guide. Then the Initiation Request.

CS Template Library v1.0 · August 2026

Something wrong with this template? Tell us which one and what happened: backoffice@changespecialists.co.uk