## How to use
Programme Health Check
Governance · Finances · Risks · Benefits
| What this is | A structured assessment of whether a programme is actually in control. Four areas, scored against evidence, with a finding and a recommendation for anything weak.
| The four phases | PREPARATION — agree what you are assessing, gather the documents, identify who to talk to. ASSESSMENT — work through the questions, evidence each one. REPORTING — a short report with prioritised recommendations. FOLLOW-UP — check the recommendations were acted on. Most health checks fail at the fourth.
| Score against evidence | 1 = absent or failing. 2 = there in name only. 3 = works, with gaps. 4 = solid. 5 = strong, and you saw it working. Score what you saw, not what you were told.
| The Evidence column is not optional | A score with no evidence is an opinion. If you cannot say what you saw, you have not assessed it — mark it 1 and say so, or leave it blank and use N/A.
| Use N/A honestly | Some questions genuinely will not apply. Mark them N/A and they drop out of the average. Marking something N/A because it scores badly is how a health check becomes a comfort blanket.
| A low score needs a recommendation | Anything scoring 1 or 2 with no recommendation is flagged. Finding a problem and not saying what to do about it is half a job.
| Note on the scale | This scale runs the OPPOSITE way to the RAID log and the Change Impact Assessment. Here 5 is good, because it measures strength. There a high number is bad, because it measures exposure. Worth saying out loud so the two are not read the same way.
| Where this scale comes from | The four areas and the four phases are CS method, published on the Knowledge Centre. The 1-5 scoring is this template's own convention — CS has not published a scoring scale, and this workbook does not pretend otherwise. Change it if your programme needs something different.
| Then what | The Summary tab gives you a score per area and the recommendations in priority order. That is your report. Re-run the check after the follow-up period and compare.
| Change Specialists | EXPERIENCE ¦ KNOWLEDGE ¦ RESULTS
Where this sits
Comes from: A programme in trouble, or Taking Over A Programme.
Feeds: The Assurance Review, the RAID Log and a recovery plan.
CS Template Library v1.0 · August 2026
Something wrong with this template? Tell us which one and what happened: backoffice@changespecialists.co.uk

## Summary
Health Check Summary
< How to use | Scores update automatically. Nothing to fill in.
| Area | Scored | Average | RAG | Read it as
Governance
Finances
Risks
Benefits
Overall
Quality of this check
| Not yet scored |  |  |  | Questions with no score and not marked N/A.
| Marked not applicable |  |  |  | Fine if genuine. A lot of these makes the averages meaningless.
| Scored with no evidence |  |  |  | A score with no evidence is an opinion, not a finding.
| Weak scores with no recommendation |  |  |  | Finding a problem and not saying what to do about it is half a job.
| Recommendations with no owner |  |  |  | Same rule as the RAID log. Without an owner it will not happen.
| Change Specialists | EXPERIENCE ¦ KNOWLEDGE ¦ RESULTS

## Assessment
Programme Health Check
Score what you saw, not what you were told.
< How to use
Ref | Area | What good looks like | Score 1-5 | N/A | Evidence — what did you see? | Finding | Recommendation | Owner | By when
| Governance | There is a named sponsor who is engaged, not just listed.
| Governance | The board meets to a cadence and makes decisions when it meets.
| Governance | Decisions are recorded, with who took them and why.
| Governance | Escalation paths are known and are actually used.
| Governance | Roles are clear — people know what they are accountable for.
| Governance | Stage gates exist and something can actually fail one.
| Governance | Change control is followed, not bypassed for urgent items.
| Governance | Reporting reaches the people who can act on it.
| Finances | There is an approved budget and everyone works to the same number.
| Finances | Actuals are tracked against forecast, at least monthly.
| Finances | Variance is explained rather than just reported.
| Finances | Committed spend is visible, not just invoiced spend.
| Finances | The forecast to completion is re-done, not carried forward.
| Finances | Contingency is held, and drawing on it needs a decision.
| Finances | The cost of the business change is in the budget, not only the build.
| Risks | A RAID log exists and was updated in the last month.
| Risks | Every entry has a named owner.
| Risks | Risks are ranked by impact and likelihood, not by who raised them.
| Risks | Mitigations are actions with dates, not intentions.
| Risks | Issues are resolved rather than carried indefinitely.
| Risks | Dependencies outside the programme are tracked and chased.
| Risks | Bad news travels upward without being softened.
| Risks | Assumptions are written down and have validation dates.
| Benefits | The benefits in the business case are still credible today.
| Benefits | Each benefit has a named owner in the business, not in the programme.
| Benefits | Measures are baselined, so improvement could be shown.
| Benefits | Benefits are tracked after go-live, not only forecast before it.
| Benefits | The people who must work differently know what that means for them.
| Benefits | Adoption is measured — usage AND proficiency, not attendance.
| Benefits | Qualitative signals are watched: sentiment, behaviour, change fatigue.
| Benefits | Someone is accountable for benefits after the programme closes.