## How to use
CS RAID Log
Risks · Assumptions · Issues · Dependencies
| What this is | A single log for the four things that decide whether a programme stays in control: risks, assumptions, issues and dependencies. One tab each, because each needs different information.
| Start here | Use the Dashboard tab. It counts everything for you and tells you where to look first. You do not need to fill anything in on the Dashboard.
The one rule that matters
Every entry needs a named owner. An entry without a named owner is a note, not a control. The log highlights any entry missing one, and the Dashboard counts them.
What goes in each tab
| Tab | What it holds | The fields it needs
| Risks | Something that might happen and would hurt if it did. | Description · potential impact · likelihood · mitigation plan · owner
| Assumptions | Something being taken as true that has not been proven. | Description · consequence if it proves false · the date it will be validated · owner
| Issues | Something that has already happened and needs resolving. | Description · effect if unresolved · priority · resolution plan · owner
| Dependencies | Something outside your control that you need. | Description · what happens to the programme if it is not met · due date · owner
What a good entry looks like
Vague entries are the commonest failure. Compare these two risks.
| Not good enough | Risk: resourcing. Impact: high. Owner: the team.
| Good | Risk: the two integration testers are booked onto another release from 6 October, leaving no cover for system test. Potential impact: system test slips two weeks and the November release date is missed. Likelihood 4, Impact 4. Mitigation: confirm backfill by 15 September or move the release. Owner: named individual. Target date: 15 September.
How the colours work
• Risks — score is likelihood multiplied by impact. 15 or more is Red, 8 to 14 is Amber, below 8 is Green.
• Assumptions and Dependencies — Red once the date has passed, Amber within 14 days of it, Green otherwise.
• Issues — Red if Critical or High, or if the target date has passed. Amber if Medium.
• A missing owner turns the Owner cell red on any tab.
Business adoption
Risks and Issues carry a business adoption flag. Use it whenever the entry would affect whether people actually take the change on — not just whether it is delivered. Delivery risk and adoption risk are not the same thing, and adoption risk is the one that usually gets missed. The Dashboard counts them separately.
The formula and ID columns are locked so they are not overwritten by accident. There is no password — use Review › Unprotect Sheet if you need to change the structure.
Where this sits
Comes from: The Project Charter or Programme Brief, from day one.
Feeds: The Project Status Report, the Risk Register for anything scored high, and the Decision Log.
CS Template Library v1.0 · August 2026
Something wrong with this template? Tell us which one and what happened: backoffice@changespecialists.co.uk

## Dashboard
RAID Dashboard
< How to use | Counts update automatically. Nothing here needs filling in.
|  | Entries | Red | Amber | Open | Where to look
Risks
Assumptions
Issues
Dependencies
Controls
| Entries with no owner |  |  |  |  | An entry without a named owner is a note, not a control. This should be zero.
| Flagged as affecting business adoption |  |  |  |  | Delivery risk and adoption risk are not the same thing. This is the one that usually gets missed.
| Risks not reviewed in 30 days |  |  |  |  | A RAID log nobody revisits stops being a control.
| Change Specialists | EXPERIENCE ¦ KNOWLEDGE ¦ RESULTS

## Risks
RAID Log — Risks
Something that might happen and would hurt if it did.
< How to use
ID | Date raised | Description | Potential impact | Likelihood 1-5 | Impact 1-5 | Score | RAG | Mitigation plan | Owner | Target date | Status | Affects business adoption? | Last reviewed | Days since review
Formulas:
Days since review = IF(OR([Description]="",[Last reviewed]=""),"",TODAY()-[Last reviewed])

## Assumptions
RAID Log — Assumptions
Something being taken as true that has not been proven.
< How to use
ID | Date raised | Description | Consequence if it proves false | Validation date | Owner | Status | RAG
Formulas:
RAG = IF([Description]="","",IF([Status]="Validated - true","Green",IF([Status]="Validated - false","Red",IF([Validation date]="","Amber",IF([Validation date]<TODAY(),"Red",IF([Validation date]-TODAY()<=14,"Amber","Green"))))))

## Issues
RAID Log — Issues
Something that has already happened and needs resolving.
< How to use
ID | Date raised | Description | Effect if unresolved | Priority | Resolution plan | Owner | Target date | Status | Affects business adoption? | RAG
Formulas:
RAG = IF([Description]="","",IF([Status]="Closed","Green",IF(OR([Priority]="Critical",[Priority]="High"),"Red",IF(AND([Target date]<>"",[Target date]<TODAY()),"Red",IF([Priority]="Medium","Amber","Green")))))

## Dependencies
RAID Log — Dependencies
Something outside your control that you need.
< How to use
ID | Date raised | Description | Impact on the programme if it is not met | Due date | Owner | Status | RAG
Formulas:
RAG = IF([Description]="","",IF([Status]="Met","Green",IF([Status]="At risk","Red",IF([Due date]="","Amber",IF([Due date]<TODAY(),"Red",IF([Due date]-TODAY()<=14,"Amber","Green"))))))